## MIS
Task Plan April- 2023/ Dept: MIS
Sl. | Project | Component | Task | Responsibility | Date | Value | Status | Remarks
1 | LAMS(AM/NS) | Mobile APP Commissioning | JAVA API Services | Barsha Rani | 2023-04-25 | 15.5
2 | LAMS(AM/NS) | Mobile APP Commissioning | App Development | Suraj | 2023-04-25
3 | OSDI | Database Finalization | Hemgiri P.G Devlp | Ilu | 2023-04-25 | 22.5 | Completed
4 | OSDI | Database Finalization | Final GeoDB of BMC & Hemgiri | Ilu | 2023-04-25 | 45 | Completed
5 | OSDI | Database Finalization | DB Intg & Final Geo portal | Abhas | 2023-04-25 | 22.5 | Completed
6 | OSDI | Application Acceptance | Web App Go-Live | Bishal, Saurav, Ranjan | 2023-04-03 | 90 | Completed
7 | OSDI | Application Acceptance | Mobile App Go Live | Riaz, Tapas, Mohsina | 2023-04-03 |  | Completed
8 | OSDI | Training | Training Web/Mobile | Bishal, Riaz | 2023-04-25 | 22.5
9 | SLTP | 2nd Phase QC | QC- 10 Divisions | Chinmaya, Rashmi Lenka | 2023-04-25 | 30.54
10 | Land Management (LIS) | Presales Support | POC | Abhas, Bibek | 2023-04-25 | TBD
11 | Land Management (LIS) | Presales Support | Prototype | Bibek, Laxmikant, Tarini | 2023-05-15 | TBD
12 | Minescope | Presales Support | POC | Abhas, Bibek | 2023-04-30 | TBD
13 | Minescope | Presales Support | Prototype | Bibek, Laxmikant, Tarini | 2023-05-15 | TBD
14 | ForestScope(GRFL) | Presales Support | POC | Abhas, Deepak | 2023-04-21 | TBD
|  |  |  | Total |  | 248.54

## FC
Task Plan April- 2023/ Dept: FC Unit
Sl. | Project | Component | Resp | Date | Value (L) | Status | Remarks
1 | AMNS | ORSAC Certification | Santosh | 2023-04-20 | 51
2 | AMNS | Additional Land schedule Certification | Santosh | 2023-04-03 |  | Completed
3 | AMNS | DGPS Maps Corection as per new area | Nikunja | 2023-04-07 |  | Completed
4 | AMNS | Map submission to AMNS | Santosh | 2023-04-07 |  | Completed
5 | AMNS | DGPS Maps forwarding to ORSAC through DFO, Rajnagar | Sisir | 2023-04-10 |  | Completed
6 | AMNS | Verification at ORSAC and issue of Demand | Asish | 2023-04-17
7 | AMNS | Fund deposite by AMNS | AMNS | 2023-04-20 |  | YTS
8 | AMNS | Receive certified Map from ORSAC | Asish | 2023-04-20 |  | YTS
9 | AMNS | E-Filling | Santosh | 2023-04-25 | 51
10 | AMNS | Draft Proposal submission to AMNS | Santosh | 2023-04-10 |  | Completed
11 | AMNS | Approval of Proposal by AMNS | Santosh | 2023-04-19
12 | AMNS | Draft E-filling | Prabhat | 2023-04-20 |  | Completed
13 | AMNS | Final Fillig (Save & lock) | Prabhat | 2023-04-22 |  | YTS
14 | IDCO-KN | Part-II & Obtaining FRA certificate-20% | Prabhat | 2023-04-25 | 62.14
15 | IDCO-KN | Re authentication of Joint verification reports maps form concerned revunue & forest staffs | Prabhat | 2023-04-10 |  | Completed
16 | IDCO-KN | CAF Scheme formulation | Prabhat | 2023-04-24 |  | YTS
17 | IDCO-KN | Joint verification of Project area by DFO | Prabhat | 2023-04-28 |  | YTS
18 | IDCO-KN | Proposal forwarding from DFO to RCCF | Prabhat | 2023-05-04 |  | YTS
19 | SJIA_Puri | E-Filling | Santosh | 2023-04-13 | 14.02 | Completed | Bill to be raise
20 | SJIA_Puri | Verification at ORSAC and issue of Demand | Santosh | 2023-03-28 |  | Completed
21 | SJIA_Puri | Fund deposite by IDCO | Santosh | 2023-04-05 |  | Completed
22 | SJIA_Puri | Receive certified Map from ORSAC | Santosh | 2023-04-10 |  | Completed
23 | SJIA_Puri | Draft Proposal submission to IDCO | Santosh | 2023-04-10 |  | Completed
24 | SJIA_Puri | Approval of Proposal by IDCO | Santosh | 2023-04-12 |  | Completed
25 | SJIA_Puri | Draft E-filling | Santosh | 2023-04-10 |  | Completed
26 | SJIA_Puri | Final Fillig (Save & lock) | Santosh | 2023-04-13 |  | Completed
27 | SJIA_Puri | Part-II & Obtaining FRA certificate-20% |  | 2023-04-30 | 14.02
28 | SJIA_Puri | Meeting with the PSC | Santosh | 2023-04-19 |  | YTS
29 | SJIA_Puri | Compliance to the observation of PSC | Santosh | 2023-04-25 |  | YTS
30 | SJIA_Puri | Tree enumeration & Pillar posting Complition | Santosh | 2023-04-25 |  | YTS
31 | SJIA_Puri | Site Inspection by DFO, Puri | Santosh | 2023-04-29 |  | YTS
32 | SJIA_Puri | Proposal forwarding from DFO to RCCF | Santosh | 2023-04-30 |  | YTS
33 | OCCL_Kala | Pillar posting Certification | Ajit | 2023-04-20 | 19.52 | Completed | Bill to be raise on monday
34 | OCCL_Kala | Site Inspection by RO, Barkote | Ajit | 2023-04-10 |  | Completed
35 | OCCL_Kala | Verification by DoWR Officials | Ajit | 2023-04-15 |  | Completed
36 | OCCL_Kala | Report Authentication | Ajit | 2023-04-20 |  | Completed
37 | OCCl_Jeera | Stage-II approval | Ashish | 2023-04-25 | 2
38 | OCCl_Jeera | Stage-I Compliance forwarding from PCCF to MoEF & CC | Ashish | 2023-04-04 |  | Completed
39 | OCCl_Jeera | Stage-II approval from MoEF & CC | Ashish | 2023-04-25
40 | ECoR (BDPK-SQQ) | Stage-II approval | Santosh | 2023-04-10 | 9.31 | Completed | Bill to be raise on monday
41 | ECoR (BDPK-SQQ) | Submission of handing Over documents to EcoR & acceptance of Bill | Santosh | 2023-04-10 |  | Completed
42 | OCCL_Turi | ORSAC Certification | Ashish | 2023-04-20 | 9.73
43 | OCCL_Turi | Fund deposite by SE, Koraput | Ashish | 2023-04-20
44 | OCCL_Turi | Receive certified Map from ORSAC | Ashish | 2023-04-20
|  | Total |  |  | 232.74

## Paddy
Task Plan April- 2023/ Dept: Paddy Project
Sl. | Component | Resp. | Date | Value (L) | Status | Remarks
1 | Farmer DB, cadastral editing, Farmer DB linking, Cr/NCr classification | ILU | 2023-04-04 | 134 | Complete | Submitted by 06-04-2023/ Billing Pending
2 | Collection of pending hal cadastral maps | ILU | 2023-04-15
3 | Collection of reported farmer database and sanitize | Laxmi | 2023-04-07 |  | Complete
4 | Cadastral mapping of Rabi reported crops | ILU | 2023-04-25 | 201.6
5 | Linking and sub-division of plots reported Rabi database_141 Tah. | Team | 2023-04-15
6 | Hal map digitization_15000 Plts, 150 maps | Saswati & Team
7 | Geo-referencing | Saswati & Team | 2023-04-17 |  | Complete
8 | Cadastral map for rabi reported plots | Laxmi | 2023-04-23 |  | Complete
9 | Collection of HRSI through ORSAC | ILU | 2023-04-10 |  | Complete
10 | HRSI Image Analysis Delivery (Lot 1: BARGARH, BALASORE, PURI, SAMBALPUR, KALAHANDI._5 dist, 53 tahsils) | ILU | 2023-04-18 |  |  | Bargarh, Balasore, Puri, Sambalpur published
11 | DO (Lot 2:CUTTACK, SUBARNAPUR, JHARSUGUDA, MAYURBHANJ, RAYAGADA, NAWARANGPUR_6 dist, 45 tahsils) | ILU | 2023-04-23
12 | DO (Lot 3:BOLANGIR, BOUDH, NUAPADA, KORAPUT, JAJPUR, KHORDHA_6 dist, 43 tahsils) | ILU | 2023-05-08 |  | Not started
|  | Total |  | 335.6

## TSF
Task Plan April- 2023/ Dept: Paddy Project
Sl. | Component | Task | Quantity | Responsibility | Date | Value | Status | Remarks
1 | Pending Ortho-Image Processing | Ortho Processing | 40 | Bikram | 2023-04-12 | 18.88 | Comp.
2 | Pending Ortho-Image Processing | Slum boundary delination | 87 | Akanshya, Sasmita | 2023-04-20 |  |  | 43-Pending(RMC)
3 | Pending Ortho-Image Processing | Ortho map preparation | 87 | Akanshya, Sasmita | 2023-04-21 |  |  | 43-Pending(RMC)
4 | Pending Ortho-Image Processing | Ortho Map Submission for HH survey | 87 | Akanshya, Sasmita | 2023-04-22
5 | Draft settlement map with area statement of all Corporation | Structure Digitization | 535 | Madhu B & Team-10 | 2023-04-28 | 237
6 | Draft settlement map with area statement of all Corporation | Revenue integration with ROR | 535 | Manasi, Priyanka S, Ankita-3 | 2023-04-26
7 | Draft settlement map with area statement of all Corporation | Generate Area Statement | 535 | Subhasree, Ayutu | 2023-04-27
|  |  |  | Total |  | 255.88

## CDLTP
Task Plan April- 2023/ Dept: CDLTP Unit
Sl. | Project | Component | Area (Sq Km ) | Resp. | Date | Value (L) | Status | Remarks
1 | Dhenkanal | JV | 300 | Dhaban | 2023-04-27 | -
2 | Mahanadi WL | JV | 150 | Ranjeeb | 2023-04-25 | -
3 | Satkosia WL | JV | 100 | Chandan | 2023-04-25 | - | YTS
4 | Berhampur | JV | 240 | Ambedkar | 2023-04-25 | -
5 | Ghumusur North | JV | 310 | Bibhuti | 2023-04-25 | -
6 | Ghumusur South | JV | 300 | Bibhuti | 2023-04-25 | -
7 | Bolangir | JV Map Submission FITGC | 200 | Jyotirekha | 2023-04-25 | -
8 | Khariar | JV | 220 | Sillu | 2023-04-25 | -
9 | Sunabeda WL | JV | 150 | Sillu | 2023-04-25 | -
10 | Bhadrak WL | JV Map Submission FITGC | 69 | Madhu N | 2023-04-25 | -
11 | Chilika WL | JV | 100 | Puneysh | 2023-04-25 | -
12 | Nayagarh | JV | 150 | Ranjeeb | 2023-04-25 | -
13 | Malkanagiri | CMV/MMV | - | Suresh | 2023-04-20 | 37.18
14 | Malkanagiri | JV | 150 | Suresh | 2023-04-25 |  | YTS
15 | Nabarangapur | CMV/MMV | - | Biswajeet | 2023-04-20 | 27.17 | CO
16 | Nabarangapur | JV | 150 | Biswajeet | 2023-04-25 |  | YTS
17 | Bonai | CMV/MMV |  | Sandip | 2023-04-20 | 28.89
18 | Bonai | JV | 200 | Sandip | 2023-04-25 |  | YTS
19 | Deogarh | JV | 350 | Subhrajit | 2023-04-25
20 | Bamra WL | JV | 200 | Sumit | 2023-04-25
21 | Ath | draft/geo DB | 120 | Rabi | 2023-04-20 | 7.938
22 | Ath | Rev/DLC QC |  | Rabi | 2023-04-20 | 0.76027
23 | Ath | `Closure |  | Ashok | 2023-04-20 | 0.76027
24 | Ctc | frjvc | 19 | Suvendu | 2023-04-20 | 0.69825
25 | Bali | frjvc | 140 | Sudhanshu | 2023-04-20 | 4.459
26 | Bali | draft/geo DB | 225 | Rabi | 2023-04-20 | 18.4889
27 | Bou | draft/geo DB | 400 | Rabi | 2023-04-20 | 22.932
28 | Kala S | draft/geo DB | 740 | Rabi | 2023-04-20 | 48.951
29 | Cha WL | draft/geo DB | 100 | Rabi | 2023-04-20 | 6.741
30 | Puri WL | draft/geo DB | 84 | Rabi | 2023-04-20 | 5.6624
31 | Ray | frjvc | 982 | Ramesh | 2023-04-20 | 31.2767
32 | Ray | draft/geo DB | 750 | Rabi | 2023-04-20 | 42.9975
33 | Keo | frjvc | 289 | Bijay | 2023-04-20 | 9.2047
34 | Keo | draft/geo DB | 500 | Rabi | 2023-04-20 | 28.665
35 | Rdkl | Rev/DLC QC |  | Rabi | 2023-04-20 | 3.5982
36 | Rdkl | Closure |  | Ashok | 2023-04-20 | 3.5982
|  | Total | 7688 |  |  | 329.9715

## GIS
Task Plan April- 2023/ Dept: GIS Unit
Sl. | Project | Component | Resp | Date | Value (L) | Status | Remarks
1 | IDCO- Tourism | Submission of Final Base Map for 19 sites | Jogesh & Pradeep | 2023-04-15 | 39.83 |  | 7/19 Submitted
2 | IDCO- Tourism | Preparation of Land schedule of 19 sites | Jashmin, Aisha, Rashmita | 2023-04-05 |  | Completed
3 | IDCO- Tourism | Map Preparation | Jashmin, Aisha, Rashmita | 20/04
4 | IDCO- Tourism | Followup for joint meeting for FBM approval | Jogesh & Braja | 2023-04-29 |  |  | DoT
5 | IDCO- Tourism | JV for remaining 3 sites including RI & Tahsil level Certification | Jogesh, Braja, Sumit | 2023-04-25
6 | AMNS (Phase 1) | Drone Survey | Braja & Sumit | 2023-04-15 |  | Completed | Survey completed
7 | AMNS (Phase 1) | Image processing & submission | Bikram & Braja | 2023-05-20 | 13.65
8 | Impal Georeferencing & Mapping | Geo referencing of cadastral maps (119 Nos) | Jogesh | 2023-04-20 | 6.175
9 | Impal Georeferencing & Mapping | Digitisation of Revenue sheets | Sabitri & Rashmita | 2023-04-24
10 | Impal Georeferencing & Mapping | Preparation of Land Plan | Jogesh | 2023-04-28 | 3.08
62.735

## HR
Task Plan April- 2023/ Dept: HR Unit
Sl. | Purpose | Dept | Activity | Qty. | Date | Resp | Support | Status | Remarks
1 | General | Internal | Renewal of Naukri account |  | 2023-04-19 | Rosy | Swati
2 | Joining | MIS | Sr. Graphics Designer | 1 no. | 2023-04-15 | Rosy |  | Completed
3 | Recruitment | MIS/GIS | Project Manager | 2 nos. | 2023-04-20 | Rosy
4 | Recruitment | GRFL | Surveyors | 20 nos. | 2023-04-25 | Abhipsa | Rosy
5 | Recruitment | GRFL | Field Coordinators | 5 nos. | 2023-04-15 | Abhipsa | Rosy | Completed
6 | Recruitment | GRFL | GIS Analyst | 15 no.s | 2023-04-30 | Madhu-J | Rosy
7 | Recruitment | FC | Field Coordinators | 4 nos. | 2023-04-15 | Rosy | Madhu-J
8 | Recruitment | MIS | Fullstack Developer | 3 nos. | 2023-04-25 | Rosy | Priyanka
9 | Recruitment | MIS | Software Dev (Freshers) | 4 nos. | 2023-04-10 | Rosy | Priyanka | Completed
10 | Recruitment | MIS | UI/UX Dev | 1 no. | 2023-04-15 | Rosy | Priyanka
11 | Recruitment | MIS | Android dev | 1 no. | 2023-04-20 | Rosy | Priyanka
12 | Recruitment | MIS | IOS dev | 1 no. | 2023-04-25 | Rosy | Priyanka
13 | Recruitment | BD | Sales | 2 nos. | 2023-04-25 | Rosy | Swati
14 | Recruitment | BD | Presales | 2 nos. | 2023-04-25 | Rosy | Swati
15 | Recruitment | HR | HR Interns | 3 nos. | 2023-04-25 | Rosy | Swati
16 | Evaluation | Review & Evaluation | Trainees/ Intern | 4 nos. | 2023-04-15 | Concerned HR | Rosy
17 | Evaluation | Review & Evaluation | Probation | 4 nos. | 2023-04-15 | Concerned HR | Rosy | Completed
18 | Skill Development | Internal | Business Communication Programme | 30 nos. | 2023-04-30 | Swati | -
19 | Skill Development | BD | Induction Training for PR | 1 no. | 2023-04-30 | Swati
20 | Documentation | Internal | As per requirement |  |  | Swati
21 | Exit | Internal | As per requirement |  |  | Rosy
22 | Project Coordination | GRFL | As per requirement |  |  | Abhipsa
23 | Project Coordination | MIS/SLUM | As per requirement |  |  | Priyanka
24 | Project Coordination | GIS/FC/GIS(Lab) | As per requirement |  |  | Madhu

## BD
Task Plan April- 2023/ Dept: BD Unit
Sl. | Client | Project Name | Purpose | Date | Price (INR) | Remarks
1 | ORSAC- SJTA | ORSAC - Development of Web and Mobile GIS Land Bank Application for Shree Jagannath Temple Administration | Bid finalization | 15th April |  | SPARC documentation 90% done and CSM will share the document by 17th April
2 | ORSAC- SJTA | SPARC(Lead) & CSM | Tech PPT finalization | 17th April
3 | ORSAC- SJTA | SPARC(Lead) & CSM | Bid Submission | 21st April
4 | ORSAC- SJTA | STL(Lead) & PAN Supporting Bid | Bid finalization | 13th April |  | PAN documentation completed
5 | ORSAC- SJTA | STL(Lead) & PAN Supporting Bid | Tech PPT finalization | 15th April
6 | ORSAC- SJTA | STL(Lead) & PAN Supporting Bid | Bid Submission | 20st April
7 | ORSAC- SJTA | GeoCon(Lead) & OYSIS Supporting Bid | Bid finalization | 12th April |  | GeoCon documentation completed
8 | ORSAC- SJTA | GeoCon(Lead) & OYSIS Supporting Bid | Tech PPT finalization | 14th April
9 | ORSAC- SJTA | GeoCon(Lead) & OYSIS Supporting Bid | Bid Submission | 20st April | 10 Crores
10 | IDCO_KNIC | Kalinganagar Industrial complex (KNIC) Land Bank Application |  | 14th April | 21 Lakhs
11 | FDP_GTM | Forest Diversion Proposal – Draft GTM Presentation |  | 23th April |  | Draft PPT completed
12 | OCC_Kharibandhan | Additional Work Karibandahan |  | 27th April | 90 Lakhs
13 | AMNS | AM/NS Phase II Development of Draft ToR |  | 29th April | ------------ | Draft Ongoing
Minimum Client Visit- 10 Nos. for FDP

## Revenue
Task Plan April- 2023/ Dept: Revenue
Sl. | Project | Value | By Date | Remarks
Old Outstanding
1 | UFRMP | 1.44 | 2023-04-12 | Completed
2 | OCC_Ranjore | 2 | 2023-04-15 | Fund allotment not available
3 | OCC_Korapani | 9.25 | 2023-04-15 | Fund allotment not available
4 | OCC_SSAP | 10.29 | 2023-04-15 | Fund allotment not available
5 | IDCO_Kalingnager | 46.6 | 2023-04-25 | Work to be delivered
6 | ECoR B-S | 8.61 | 2023-04-04 | Completed
7 | ORSAC_MP_CC (binaya) | 0.5 | 2023-04-20
8 | OFSDP_MIS | 4.62 | 2023-04-20 | Work to be delivered
9 | GRFL- Final ROR & DLC -P2 |  | 2023-04-20 | Technical compliance- pending
10 | OCC_Ranjore | 3.01 | 2023-04-15
11 | OFSDP-2nd beta | 9.25 | 2023-04-20 | Work to bedelivered
12 | ORSAC_MP_CC(binaya) | 0.5 | 2023-04-20
13 | ORSAC_MP_CC (binaya) | 0.5 | 2023-04-20
| Rodic | 3.08 | 2023-04-17 | Completed
New Outstanding
14 | Paddy | 780.05 | 2023-04-15 | Completed
15 | UFRMP | 20.32 | 2023-04-25
| Total | 900.02

## Accounts
Task Plan April- 2023/ Dept: Account
Sl | Description | Completed By | Status
FY-2022-23
1 | GSTR-1 Filing March'23 | 2023-04-11 | Completed
2 | GSTR-2B Computation & Reconciliation | 2023-04-15 | Completed
3 | GST Deposit and GSTR-3B filing | 2023-04-20
4 | TDS Deposit Mar'2023 | 2023-04-29
5 | EPF Deposit & Filing | 2023-04-15 | Completed
6 | ESI Deposit & Filing | 2023-04-15 | Completed
7 | Professional Tax Deposit | 2023-04-15 | Completed
8 | TDS Receivable & Payable Reconcliation with Form 26AS | 2023-04-15
9 | Sundry Debtor & Creditor Reconciliation. | 2023-04-25
10 | All Bank Account/ Loans/ FD/ BG Reconciliation. | 2023-04-15
11 | TDS Filing Q4 FY 2022-23 | 2023-05-15
12 | Form 16A & 16B generation | 2023-05-18
FY-2023-24
1 | SPARC Annual Budget for 23-24 | 18/04/2023
2 | Departmental Budget Fy 23-24 | 15/04/2023

## Billing
Projected Billing -April 2023
Sl. | Project | Component | Task | Resp. | Date | Value | Remarks
Dept: MIS Unit
1 | LAMS(AM/NS) | Mobile APP Commissioning | JAVA API Services | Barsha Rani | 2023-04-25 | 15.5
2 | OSDI | Database Finalization | Hemgiri P.G Devlp | Ilu | 2023-04-25 | 22.5
3 | OSDI | Database Finalization | Final GeoDB of BMC & Hemgiri | Ilu | 2023-04-25 | 45
4 | OSDI | Database Finalization | DB Intg & Final Geo portal | Abhas | 2023-04-25 | 22.5
5 | OSDI | Application Acceptance | Web App Go-Live | Bishal, Saurav, Ranjan | 2023-04-03 | 90
6 | OSDI | Training | Training Web/Mobile | Bishal, Riaz | 2023-04-25 | 22.5
7 | SLTP | 2nd Phase QC | QC- 10 Divisions | Chinmaya, Rashmi Lenka | 2023-04-25 | 30.54
|  |  |  | SubTotal |  | 248.54
Dept: FC Unit
1 | AMNS | ORSAC Certification |  | Santosh | 2023-04-20 | 51
2 | AMNS | E-Filling |  | Santosh | 2023-04-25 | 51
3 | IDCO-KN | Part-II & FRA certificate-20% |  | Prabhat | 2023-04-25 | 62.14
4 | SJIA_Puri | E-Filling |  | Santosh | 2023-04-13 | 14.02 | Billed
5 | SJIA_Puri | Part-II & FRA certificate-20% |  |  | 2023-04-30 | 14.02
6 | OCCL_Kala | Pillar posting Certification |  | Ajit | 2023-04-20 | 19.52 | Billed
7 | OCCl_Jeera | Stage-II approval |  | Ashish | 2023-04-20 | 2
8 | ECoR (BDPK-SQQ) | Stage-II approval |  | Santosh | 2023-04-10 | 9.31 | Will competed by 18April
9 | OCCL_Turi | ORSAC Certification |  | Ashish | 2023-04-15 | 9.73 | delay in deposit of money by user agency
|  |  |  | SubTotal |  | 232.74
Dept: CDLTP
1 | Malkanagiri | CMV/MMV | - | Suresh | 2023-04-20 | 37.18
2 | Nabarangapur | CMV/MMV | - | Biswajeet | 2023-04-20 | 27.17 | Completed,To be billed
3 | Bonai | CMV/MMV |  | Sandip | 2023-04-20 | 28.89
4 | BMW | CMV/MMV |  |  | 2023-04-10 | 21.88 | Completed, To be billed
5 | Ath | draft/geo DB | 120 | Rabi | 2023-04-20 | 7.938
6 | Ath | Rev/DLC QC |  | Rabi | 2023-04-20 | 0.76027
7 | Ath | Closure |  | Ashok | 2023-04-20 | 0.76027
8 | Ctc | frjvc | 19 | Suvendu | 2023-04-20 | 0.69825
9 | Bali | frjvc | 140 | Sudhanshu | 2023-04-20 | 4.459
10 | Bali | draft/geo DB | 225 | Rabi | 2023-04-20 | 18.4889
11 | Bou | draft/geo DB | 400 | Rabi | 2023-04-20 | 22.932
12 | Kala S | draft/geo DB | 740 | Rabi | 2023-04-20 | 48.951
13 | Cha WL | draft/geo DB | 100 | Rabi | 2023-04-20 | 6.741
14 | Puri WL | draft/geo DB | 84 | Rabi | 2023-04-20 | 5.6624
15 | Ray | frjvc | 982 | Ramesh | 2023-04-20 | 31.2767 | 185.43 Sq.Km completed
16 | Ray | draft/geo DB | 750 | Rabi | 2023-04-20 | 42.9975
17 | Keo | frjvc | 289 | Bijay | 2023-04-20 | 9.2047 | 59.64 Sq. km completed
18 | Keo | draft/geo DB | 500 | Rabi | 2023-04-20 | 28.665
19 | Rdkl | Rev/DLC QC |  | Rabi | 2023-04-20 | 3.5982
20 | Rdkl | Closure |  | Ashok | 2023-04-20 | 3.5982 | Submitted by 06-04-2023/ Billing Pending
|  |  |  | SubTotal |  | 351.8515
Dept: Paddy
1 | Paddy | Farmer DB, cadastral editing, Farmer DB linking, Cr/NCr classification |  | ILU | 2023-04-04 | 134
2 | Paddy | Cadastral mapping of Rabi reported crops |  | ILU | 2023-04-25 | 201.6
|  |  |  | SubTotal |  | 335.6
Dept: GIS
1 | IDCO- Tourism | Submission of Final Base Map for 19 sites |  | Jogesh & Pradeep | 2023-04-10 | 39.83
2 | AMNS (Phase 1) | Drone Survey |  | Braja & Sumit | 2023-04-10 | 13.65
3 | Impal Georeferencing & Mapping | Geo referencing of cadastral maps (119 Nos) |  | Nikunja & Jogesh | 2023-04-17 | 6.175
4 | Impal Georeferencing & Mapping | Preparation of Land Plan |  | Jogesh & Pradeep | 2023-04-25 | 3.08
|  |  |  | SubTotal |  | 62.735
Dept: SLUM
1 | Pending Ortho-Image Processing | Ortho Processing | 40 | Bikram | 2023-04-12 | 18.88
2 | Draft settlement map with area statement of all Corporation | Structure Digitization | 535 | Madhu B & Team-10 | 2023-04-28 | 237
|  |  |  | SubTotal |  | 255.88
|  |  |  | Grand Total |  | 1487.3465